## Sheet1
Task Name | Start Date | End Date | Duration (Days)
Requirement gathering (functional + non-functional) | 2025-09-01 | 2025-09-03 | 3
Stakeholder analysis | 2025-09-04 | 2025-09-05 | 2
UML Use Case Diagram | 2025-09-06 | 2025-09-07 | 2
UML Class, Sequence, Activity Diagrams | 2025-09-08 | 2025-09-10 | 3
Product backlog creation (8 user stories for SAS) | 2025-09-11 | 2025-09-12 | 2
Sprint planning (tasks, story points, deadlines; Sprint 1 scope) | 2025-09-13 | 2025-09-14 | 2
Task assignment in Trello (assign Rohit, Sanjog, Sujal; labels & due dates) | 2025-09-15 | 2025-09-16 | 2
Test case preparation (Unit, Integration, System, UAT) | 2025-09-17 | 2025-09-19 | 3
GitHub repo updates (requirements, design, test cases) | 2025-09-20 | 2025-09-22 | 3
Final report writing & submission (screenshots, links, APA refs) | 2025-09-23 | 2025-09-25 | 3